## Testing
MARCH
| 2017 |  |  |  |  | CALENDAR MONTH | MARCH
[6 empty] | CALENDAR YEAR | 2017
[6 empty] | 1ST DAY OF WEEK | SUNDAY
| 42792 | 42793 | 42794 | 42795 | 42796 | 42797 | 42798
| 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04
daily notes
| 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11
daily notes |  | FSRI on Site Instrument Prop 1 | Prop 1 Entrainment & Water Dist Testing | Prop 1 Entrainment & Water Dist Testing, Instrument Prop 2 | Burn 1 & 2, Demo (Remove 1 layer 1/2" gypsum), Refurnish, Reinstrument | Burn 3 & 4, Demo (Remove 1 layer 1/2" gypsum), Refurnish, Reinstrument
| 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18
daily notes | 2017-03-13: Burn 5 & 6; 2017-03-14: Demobilize
| 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25
daily notes
| 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01
daily notes
| 2017-04-02 | 2017-04-03 | Notes | TESTING SCHEDULE
daily notes

## Burn Days
Time | Event
0630-0700 | Site Arrival
0700-0900 | Instrument Checks, Final Preps
0900-0945 | First Burn
0945-1100 | Instrument Checks, Final Preps
1100-1145 | Second Burn
1145-1300 | Lunch
1300-1800 | Overhaul, Furnish, Instrument Both Props

## Air Entrainment
Experiment 1 (hall door open, BR1 window OPEN) |  | Experiment 2 (hall door open, BR1 window OPEN) |  |  | Start Hall | 4' from hall door
Time (min) | Action | Time (min) | Action |  | Mid Hall | 12' from hall door
1 | Background | 1 | Background |  | End Hall | 20' from hall door
1 | Straight Stream Fixed (start hall) | 1 | Straight Stream Fixed (start hall)
1 | Straight Stream WCW (start hall) | 1 | Straight Stream WCW (start hall) |  | INTERIOR | Completed March 7th
1 | Narrow Fog Fixed (start hall) | 1 | Narrow Fog Fixed (start hall) |  | EXTERIOR
1 | Narrow Fog 'O' (start hall) | 1 | Narrow Fog 'O' (start hall)
1 | No Action | 1 | No Action
1 | Straight Stream Fixed (mid hall) | 1 | Straight Stream Fixed (mid hall)
1 | Straight Stream WCW (mid hall) | 1 | Straight Stream WCW (mid hall)
1 | Narrow Fog Fixed (mid hall) | 1 | Narrow Fog Fixed (mid hall)
1 | Narrow Fog 'O' (mid hall) | 1 | Narrow Fog 'O' (mid hall)
1 | No Action | 1 | No Action
1 | Straight Stream Fixed (end hall) | 1 | Straight Stream Fixed (end hall)
1 | Straight Stream WCW (end hall) | 1 | Straight Stream WCW (end hall)
1 | Narrow Fog Fixed (end hall) | 1 | Narrow Fog Fixed (end hall)
1 | Narrow Fog 'O' (end hall) | 1 | Narrow Fog 'O' (end hall)
1 | Background | 1 | Background
16 | End Test | 16 | End Test
Experiment 3 (hall door open, BR1 window CLOSED)
Time (min) | Action
1 | Background
1 | Straight Stream Fixed (start hall)
1 | Straight Stream WCW (start hall)
1 | Narrow Fog Fixed (start hall)
1 | Narrow Fog 'O' (start hall)
1 | No Action
1 | Straight Stream Fixed (mid hall)
1 | Straight Stream WCW (mid hall)
1 | Narrow Fog Fixed (mid hall)
1 | Narrow Fog 'O' (mid hall)
1 | No Action
1 | Straight Stream Fixed (end hall)
1 | Straight Stream WCW (end hall)
1 | Narrow Fog Fixed (end hall)
1 | Narrow Fog 'O' (end hall)
1 | Background
16 | End Test
Experiment 4 (hall door open, BR1 window OPEN)
Time (min) | Action
2 | Background
1 | At BR1 Door, Straight Stream Fixed Max Angle
1 | At BR1 Door, Straight Stream 'O' Max Angle
1 | At BR1 Door, Straight Stream Fixed Mid Ceiling
1 | At BR1 Door, Straight Stream 'O' Mid Ceiling
1 | At BR1 Door, Straight Stream Fixed Out Window
1 | At BR1 Door, Straight Stream 'O' Out Window
1 | At BR1 Door, Straight Stream Room Sweep
2 | No Action
1 | At BR1 Door, Narrow Fog Fixed Max Angle
1 | At BR1 Door, Narrow Fog 'O' Max Angle
1 | At BR1 Door, Narrow Fog Fixed Mid Ceiling
1 | At BR1 Door, Narrow Fog 'O' Mid Ceiling
1 | At BR1 Door, Narrow Fog Fixed Out Window
1 | At BR1 Door, Narrow Fog 'O' Out Window
1 | At BR1 Door, Narrow Fog Room Sweep
1 | Background
19 | End Test
Experiment 5 (hall door OPEN, BR1 window OPEN) |  | Experiment 6 (hall door OPEN, BR1 window OPEN)
Time(min) | Action | Time(min) | Action
2 | Background | 2 | Background
1 | At Window Straight Stream Fixed | 1 | At Window Straight Stream Fixed
1 | At Window Straight Stream 'O' | 1 | At Window Straight Stream 'O'
1 | At Window Narrow Fog | 1 | At Window Narrow Fog
1 | At Window Narrow Fog 'O' | 1 | At Window Narrow Fog 'O'
1 | No Action | 1 | No Action
1 | 6' Straight Stream Fixed | 1 | 6' Straight Stream Fixed
1 | 6' Straight Stream 'O' | 1 | 6' Straight Stream 'O'
1 | 6' Narrow Fog | 1 | 6' Narrow Fog
1 | 6' Narrow Fog 'O' | 1 | 6' Narrow Fog 'O'
1 | No Action | 1 | No Action
1 | 12' Straight Stream Fixed | 1 | 12' Straight Stream Fixed
1 | 12' Straight Stream 'O' | 1 | 12' Straight Stream 'O'
1 | 12' Narrow Fog | 1 | 12' Narrow Fog
1 | 12' Narrow Fog 'O' | 1 | 12' Narrow Fog 'O'
1 | No Action | 1 | No Action
17 | Background | 17 | Background
Experiment 7 (hall door OPEN, BR1 window OPEN) |  | Experiment 8 (hall door OPEN, BR1 window OPEN) |  | Experiment 9 (hall door OPEN, BR1 window OPEN)
Time (min) | Action | Time (min) | Action | Time (min) | Action
2 | Background | 2 | Background | 2 | Background
1 | Straight Stream Max Angle | 1 | Straight Stream Max Angle | 1 | Smooth Bore Max Angle
1 | Straight Stream Max Angle Sweeping | 1 | Straight Stream Max Angle Sweeping | 1 | Smooth Bore Max Angle Sweeping
1 | No Action | 1 | No Action | 1 | No Action
1 | Narrow Fog Whip | 1 | Narrow Fog Whip | 1 | Half Bale Whip
2 | No Action | 2 | No Action | 2 | No Action
Experiment 10 (hall door OPEN, BR1 window OPEN) |  | Experiment 11 (hall door OPEN, BR1 window OPEN)
Time (min) | Action | Time (min) | Action
2 | Background | 2 | Background
1 | Smooth Bore Max Angle | 1 | Smooth Bore Max Angle
1 | Smooth Bore Max Angle Sweeping | 1 | Smooth Bore Max Angle Sweeping
1 | No Action | 1 | No Action
1 | Half Bale Whip | 1 | Half Bale Whip
2 | No Action | 2 | No Action
Experiment 12 (hall door OPEN, BR1 window OPEN) |  | Experiment 13 (hall door OPEN, BR1 window OPEN)
Time (min) | Action | Time (min) | Action
2 | Background | 2 | Background
1 | 24' Straight Stream Fixed | 1 | 24' Straight Stream Fixed
1 | No Action | 1 | No Action
1 | 48' Straight Stream Fixed | 1 | 48' Straight Stream Fixed
2 | Background | 2 | Background

## Video
Camera | Position
1 | Exterior BR1
2 | Exterior Hall
3 | BR1
4 | BR1 door
5 | Hall
6 | Hall IR
7 | BR1 Window
8 | BR1 Window IR